FORWARD DEPLOYED AI ENGINEERING

Capstone Project

Stage Four: Sprint Plan

Deciding who does what, in what order, and what finished means

A plan is not a list of tasks. It is a statement of sequence, ownership and
completion that the team has actually agreed to.

WEEK TWO · DAY ONE

How to plan three weeks of work

You have already lost a third of the project to discovery and requirements, which is as it should be. What remains has to be sequenced carefully, because several parts of the build depend on others and the dependencies are not always obvious until you hit them.

Figure 1. The shape of the three weeks, including the compulsory requirements revision.

Three rules that make the difference

Every item has an estimate in hours and a priority. When you run short of time, and you will, the priority column is what decides for you rather than whatever felt urgent that morning.

Every item has a definition of done written before work starts. Written afterwards, it describes whatever happened to be produced.

The retrieval layer and the evaluation harness come early, not late. Almost everything else depends on one or the other, and leaving the harness until the end means discovering your results too late to act on them.

The full unattended run over the hidden evaluation set happens in week two, not week three. It is the gate the project turns on, and it always exposes problems that never appear when you are testing one ticket at a time.

1   Section one: your capacity

Before you plan anything, work out honestly how much time you actually have. Plans built on optimistic capacity fail in week two rather than week three, which is worse, because by then you have committed to an architecture that assumed the time existed.

| Week | Hours realistically available | Other commitments that week | Days you cannot work |
| --- | --- | --- | --- |
| Week one | N/A -- discovery, requirements/PRD, and the full core build (ingest through guardrails, 51 tests, CI, docs) were completed in one concentrated session on 2026-09-16 rather than spread across a week. See the Effort Log for the honest accounting of this. | -- | -- |
| Week two | ~25+ hrs available across the remaining 4-5 calendar days (2026-09-16 evening through 2026-09-20), around a full-time job. NOTE: the template's 'week two' / 'week three' framing assumes a 3-week project horizon. The actual deadline is Sunday 2026-09-20 -- the full 4-part submission (report, video, workbooks + effort log, code) is due then, not in 2-3 more weeks. Section 3 below is relabelled to the real remaining days for that reason. | Full-time role at EY (weekday business hours) | None fixed -- evenings/weekend available |
| Week three | N/A -- there is no 'week three'. The deadline (2026-09-20) falls within what the template calls week two. See Section 4 below. | -- | -- |

On working alone Working individually removes the coordination overhead and replaces it with a different problem: nobody will notice when you have been stuck for six hours. Set yourself a rule that anything blocking you for more than an hour gets written down and either escalated or worked around, and check that list at the end of each day.

2   Section two: the backlog

List every item of work. Estimate in hours rather than in vague sizes, because hours can be compared against the capacity you recorded above. Mark dependencies explicitly, because the order matters more when there is only one of you.

| ID | Item | Est. hours | Priority | Depends on | Definition of done |
| --- | --- | --- | --- | --- | --- |
| B-01 | Environment and dependency setup | 2h | Critical | — | DONE. requirements.txt pinned (documented deviations from the pack's template versions), .venv, .env configured. Verified by a successful harness run end-to-end. |
| B-02 | Data loading and normalisation | 3h | Critical | B-01 | DONE. src/ingest/ingest.py normalizes all 4 channels into NormalizedTicket; never raises on missing/malformed fields. tests/test_ingest.py, 6 tests passing. |
| B-03 | Document chunking and embedding | 3h | Critical | B-02 | DONE. _chunk_document in src/retrieve/retriever.py. tests/test_retrieve_chunking.py, 4 tests passing. |
| B-04 | Vector store and retrieval | 4h | Critical | B-03 | DONE. Retriever class (Chroma + SentenceTransformer), threshold filtering at RETRIEVAL_MIN_SCORE. Verified live: 96.2% retrieval hit rate on the 2026-09-16 validation run. KNOWN GAP (disclosed, not being closed this week): the threshold-filter branch itself has no dedicated unit test. |
| B-05 | Evaluation harness | 5h | Critical | B-02 | DONE. evaluation/harness.py + evaluation/metrics.py, argparse --input/--output/--docs. Run live end-to-end on 2026-09-16 against the 80-ticket validation set: 80/80 processed, 0 ingest_errors. |
| B-06 | Intent and urgency classifier | 4h | Critical | B-02 | DONE. src/classify/classifier.py + PR-01 prompt. tests/test_classify.py, 6 tests passing. 90.0% accuracy on the live validation run. |
| B-07 | Routing logic and thresholds | 3h | Critical | B-06 | DONE. src/route/router.py, deterministic. tests/test_route.py, 7 tests passing, including a determinism test. |
| B-08 | Answer generation with citations | 4h | Critical | B-04 | DONE. src/generate/generator.py + PR-02 prompt, instruction/data separation via <ticket> tags (A6, R-03). |
| B-09 | Guardrails and validation | 4h | Critical | B-08 | DONE. src/validate/guardrails.py, 5 guardrails. tests/test_guardrails.py, 11 tests passing. KNOWN GAP (disclosed): confidence_floor_guardrail has no dedicated unit test. |
| B-10 | Decision logging | 3h | High | B-07 | DONE. src/persistence/decision_log.py, SQLite. tests/test_decision_log.py, 3 tests passing. governance_metrics() confirms decisions_logged reconciles against tickets_processed (80/80 on the live run). |
| B-11 | First full unattended run over the hidden evaluation set (THE GATE) | 2h | Critical (THE GATE) | B-05, B-09 | PARTIALLY DONE, RE-SCOPED for the real deadline. The literal hidden 120-ticket set is never available before grading -- this item can only mean 'run at full scale against the largest proxy we have before submission.' Done: live 80-ticket validation run completed and clean on 2026-09-16 after the Groq model-name fix (81.25% FCR, 18.75% escalation). NOT done and now optional given the timeline: the full 500-ticket dev-set run. Nice to have if it finishes in the background without blocking report/video work; not worth blocking on given 4 days remain. |
| B-12 | Monitoring and dashboards | 0h (cut) | CUT | B-10 | NOT STARTED. prometheus-client is pinned in requirements.txt but never imported or wired anywhere in src/ -- no /metrics endpoint, no Counter/Histogram usage exists. Explicitly cut given the 2026-09-20 deadline (see Section 5). No NFR requires a live dashboard; metrics_report.json is the system's actual reporting surface and already satisfies that need for grading purposes. |
| B-13 | Continuous integration pipeline | 2h | High | B-11 | DONE. .github/workflows/ci.yml -- installs deps, runs pytest with coverage using fakes (no live key needed), and scans for committed Groq keys (gsk_... pattern) as a separate CI step. |
| B-14 | Fairness audit | 2h | High | B-11 | PARTIALLY DONE, RE-SCOPED. fairness_segments() runs automatically inside every harness run (by customer_tier and language_fluency) -- the mechanism is built, not a manual afterthought. The 2026-09-16 80-ticket run already surfaced a real finding: a ~22-point FCR gap by customer tier (93.3% business vs. 71.4% standard) that exceeds the PRD's own 5-point NFR-06 target. Given the deadline, the root-cause investigation into WHY is cut (see Section 5); the finding itself is reported honestly in Stage 5 / the report as-is. |
| B-15 | Report, video and submission package | 20h | Critical | all | NOT STARTED. The single largest remaining item by hours: 20-30pp report (full prose, no bullets, every claim cited), ~20min video, and packaging the exact 4-folder archive structure the Submission Guide specifies. This is most of Thu-Sun (see Section 3). |
| B-16 |  | 0h (cut) | CUT |  | Add the 3 missing unit tests found during Stage 3's traceability review (confidence_floor_guardrail, the retrieval min-score branch, and the generation.declined=True -> escalate branch). Explicitly cut given the deadline -- disclosed as known, documented gaps in the report rather than closed. Depends on: B-04, B-08, B-09. |
| B-17 |  | 1h | Medium |  | Write up (not deep-investigate) the customer-tier fairness finding for the report/Stage 5, using the numbers already in hand from the 2026-09-16 run. Root-causing WHY is out of scope this week (see Section 5). Depends on: B-14. |
| B-18 |  | 1h | Medium |  | Write up (not fix) the p95 latency finding (11.5s vs. the 3s NFR-01 target, caused by Groq free-tier rate limiting under openai/gpt-oss-120b) for the report/Stage 5. Engineering a fix (batching, a smaller model, paid tier) is out of scope this week. Depends on: B-11. |
| B-19 |  | 2h | High |  | Write Stage 5 (PRD Revision Log) from the real findings above -- the fairness gap, the latency miss, and the calibration band with n=1 -- rather than from hypothetical ones. Depends on: B-14, B-17, B-18. |

3   Section three: the week two plan in detail

| Day | What will be finished by the end of the day | Hours | Risk to this |
| --- | --- | --- | --- |
| Wed 9/16 (rest of today) | Stage 4 (this workbook) and Stage 5 (PRD Revision Log) finished from real findings already in hand. Full 500-ticket dev-set eval run kicked off in the background (not blocking). | 3-4 | Stage 5 needs the fairness/latency findings to be written up clearly, not deeply investigated -- timebox this or it eats tomorrow's report time. |
| Thu 9/17 | Report writing begins: problem statement, discovery findings, PRD summary, architecture/build sections. Stage 1-3 content converts directly into most of this -- it's a rewrite into prose, not new research. Target ~40-50% of page count. | 6-7 | Prose-only (no bullets) for 20-30pp is slower to write per page than a bulleted outline -- if behind by end of day, cut scope in the later sections, not the earlier ones (discovery/PRD are already fully sourced and fastest to convert). |
| Fri 9/18 | Report draft finished: evaluation results, governance/guardrails, the fairness/latency findings (disclosed, not solved), limitations, conclusion. Video script/outline started. | 6-7 | Tightest day -- report AND video prep both need real time. If the report isn't fully done by end of Friday, video work still starts Saturday morning regardless; don't let report perfectionism eat Saturday's recording time. |
| Sat 9/19 | Record the ~20min video end-to-end (script -> screen recording of the system running live -> a clean take). Full edit pass on the report against its own rubric (every claim measured + cited, every figure numbered and captioned). | 7-8 | A clean, uninterrupted demo recording often takes several takes -- budget re-recording time rather than expecting take one to work. |
| Sun 9/20 -- SUBMIT | Final edits. Package the 4-part archive exactly per the Submission Guide's naming/folder rules (full name, no spaces, no version suffixes). Clean-checkout test on a separate venv. Credential scan. Submit with real margin before the deadline, not at the last minute. | 4-5 | The archive-naming and folder-structure rules are exact and unforgiving -- this is the highest silent-fail risk in the whole plan. Treat packaging as its own checklist item done early Sunday, not a five-minute afterthought. |

4   Section four: the week three plan in detail

| Day | What will be finished by the end of the day | Hours | Risk to this |
| --- | --- | --- | --- |
| N/A | There is no week three. The full 4-part submission is due Sunday 2026-09-20, which falls within what the template calls 'week two.' See Section 3 above for the actual day-by-day plan covering 2026-09-16 through the 2026-09-20 deadline. | -- | -- |
| N/A |  |  |  |
| N/A |  |  |  |
| N/A |  |  |  |
| N/A |  |  |  |

5   Section five: what you will drop if you run out of time

You will run out of time. Every student does. Deciding now what gets cut is far better than deciding in a panic on the final Wednesday, and it protects the parts that carry the most marks.

| Item | Cut order | Consequence of cutting it | What you will say about it in the report |
| --- | --- | --- | --- |
| B-12: Monitoring and dashboards | 1st to go | No live dashboard exists. metrics_report.json remains the sole reporting surface -- it already satisfies grading, since the harness's own report is what's actually checked. | "A live monitoring dashboard was scoped but cut given the project timeline; metrics_report.json from every evaluation run serves the same reporting function and is what this report's figures are drawn from." |
| B-16: The 3 missing unit tests found in Stage 3 | 2nd to go | The 3 gaps (confidence_floor_guardrail, the retrieval min-score branch, generation.declined branch) stay untested rather than closed. | "Three specific test-coverage gaps were identified during a traceability review (Stage 3, Section 4) and are disclosed here rather than closed, given the submission timeline: [list them explicitly]." |
| B-18: Root-causing the p95 latency miss | 3rd to go | The finding (11.5s p95 vs. the 3s NFR-01 target, caused by Groq free-tier rate limiting) is reported as-is; no engineering fix (batching, a smaller model, a paid tier) is attempted. | "NFR-01's latency target was not met under Groq's free-tier rate limits during evaluation; the cause is understood (TPM throttling on openai/gpt-oss-120b) but a fix was out of scope given the project timeline -- stated as a limitation rather than hidden." |
| B-17: Root-causing the customer-tier fairness gap | 4th to go | The finding itself (93.3% business vs. 71.4% standard FCR, a ~22-point spread against a 5-point NFR-06 target) is still reported in full -- only the deeper investigation into WHY is cut. | "A fairness gap by customer tier was found and exceeds this project's own NFR-06 target; the sample (n=42 standard, n=30 business, n=8 enterprise on the validation set) is disclosed alongside it, and root-causing it is named as the clearest candidate for follow-on work." |
| B-11 (partial): the full 500-ticket dev-set run | 5th to go | The harness's ability to run unattended at scale is already proven on the 80-ticket validation set; a larger run adds statistical confidence but is not required to demonstrate the acceptance criteria. | "Evaluation results in this report are drawn from an 80-ticket validation run; a larger 500-ticket run was started but its completion was not a hard dependency for this submission given the timeline." |

6   Section six: the daily check-in record

Ten minutes at the start of each day, answering the same three questions. Keeping this record is what makes your effort log accurate rather than reconstructed, and it is where you will notice a blocker that has quietly consumed two days.

| Date | Finished since yesterday | Doing today | Blocked by |
| --- | --- | --- | --- |
| 2026-09-16 | N/A -- day one of the real remaining runway | Fixed the Groq model-name bug (deprecated model IDs caused 100% escalation); re-ran the validation eval clean (81.25% FCR); filled Stage 3 (Prompt Library); re-planning Stage 4 around the real 2026-09-20 deadline instead of a 3-week horizon. | Learned the deadline is Sunday, not 3 weeks out, partway through planning Stage 4 -- had to re-scope the whole backlog. |